COCOMO model

Types of software development projects
- Organic projects
  - A development project can be considered of organic type, if the project deals with developing a well understood application program. This typically involves some sort of data processing program.
  - Typically the size of the development team is reasonably small, and the team members are experienced in developing similar types of projects.
- Semidetached projects
  - A development project can be considered of semidetached type, if the project deals with developing utility programs like compiler, linkers.
  - The development consists of a mixture of experienced and inexperienced staff. Team members may have limited experience on related systems but may be unfamiliar with some aspects of the system being developed.
- Embedded projects
  - A development project is considered to be of embedded type, if the software being developed is a system program.
  - System programs interact directly with the hardware and typically involve meeting timing constraints and concurrent processing.

COCOMO
COCOMO (Constructive Cost Estimation Model) was proposed by Boehm. According to Boehm, software cost estimation should be done through three stages:
- Basic COCOMO
- Intermediate COCOMO
- Complete COCOMO.

Basic COCOMO Model
The basic COCOMO model gives an approximate estimate of the project parameters. The basic COCOMO estimation model is given by the following expressions:
Effort = a_1 times (KLOC) ^{a _2} PM
Time for development = b_1 x (Effort) ^{b_2} Months
where
- KLOC is the estimated size of the software product expressed in Kilo lines of Code,
- a1, a2, b1, b2 are constants for each category of software products,
- Time for development is the estimated time to develop the software, expressed in months,
- Effort is the total effort required to develop the software product, expressed in person months (PM). A person month is the work done by a person in a month.